|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Milestone number18** | **Milestone title** | **WP**  **number9** | **Lead beneficiary** | **Due Date (in**  **months)17** | **Means of verification** |
| MS1 | MIlestone 1 | WP1, WP2, WP3, WP5 | 1 - PARTNER 1 | 12 | Metrics in Connectivity have been incorporated, tested and accepted. |
| MS2 | Milestone 2 | WP2 | 10 - PARTNER 10 | 18 | The SCM is used in a case study with at least one observational data set |
| MS3 | Milestone 3 | WP2, WP5 | 11 - PARTNER 11 | 36 | Enhanced models can be used to evaluate their predictive skill in WP5 |
| MS4 | Milestone 4 | WP3 | 7 - PARTNER 7 | 2 | The numerical experimentation plan has been updated |
| MS5 | Milestone 5 | WP4 | 3 - PARTNER 3 | 24 | Draft recommendations have been formulated |
| MS6 | Milestone 6 | WP4 | 3 - PARTNER 3 | 48 | Draft recommendations have been formulated |
| MS7 | *Milestone 7* | WP5 | 2 - PARTNER 2 | 3 | Databases for the atlas of prediction scores downloaded by the partners |
| MS8 | *Milestone 8* | WP5 | 2 - PARTNER 2 | 30 | Sensitivity experiments to improved process representation performed |
| MS9 | Milestone 9 | WP6 | 6 - PARTNER 6 | 15 | Data can be archived and external access has been setup and tested |
| MS10 | MIlestone 10 | WP7 | 13 - PARTNER 13 | 7 | Active accounts, regular updates, online visibility statistics |
| MS11 | MIlestone 11 | WP7 | 13 - PARTNER 13 | 10 | List of participants. Meeting minutes and conclusions of the User Group |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Milestone number18** | **Milestone title** | **WP**  **number9** | **Lead beneficiary** | **Due Date (in**  **months)17** | **Means of verification** |
| MS12 | Milestone 12 | WP7 | 13 - PARTNER 13 | 17 | Minutes of the meeting, Milestone suggestionsto Project Manager |
| MS13 | Milestone 13 | WP7 | 14 - PARTNER 14 | 19 | List of attendance of Milestone 13 |
| MS14 | Milestone 14 | WP7 | 13 - PARTNER 13 | 20 | Changes in the contents and structure of the website |
| MS15 | Milestone 15 | WP7 | 13 - PARTNER 13 | 35 | Minutes of the meeting, Milestone suggestionsto Project Manager |
| MS16 | Milestone 16 | WP7 | 2 - PARTNER 2 | 41 | Information made available from EU-PYTHON website |
| MS17 | Milestone 17 | WP8 | 1 - PARTNER 1 | 6 | Network of project coordinators has been established and regular teleconference have been set up |
| MS18 | Milestone 18 | WP1, WP2, WP3, WP4, WP5, WP6, WP7, WP8 | 1 - PARTNER 1 | 9 | Revised version of clustering plan after consultationwith all EU-PYTHON key partners |